## Risk Register
Risk ID | Risk Description | Category | Owner | Probability (P) | Impact (I) | PI Score | Mitigation Plan | Status
R-01 | Data breach | Security | IT Team | 10% | 5 | 0.5 | Implement firewall | Open
R-02 | Vendor delay | Operational | Operations | 30% | 3 | 0.9 | Backup vendor | In Progress
R-03 | Budget overrun | Financial | Finance | 50% | 4 | 2 | Weekly review | Closed
R-04 | AWS downtime | Operational | IT Team | 30% | 3 | 0.9 | More availability zones | In Progress
R-05 | Scope creep | Project | Project Manager | 40% | 4 | 1.6 | Strict change control | Open
R-06 | Staff shortage | HR | Operations | 20% | 3 | 0.6 | Cross-training | Open
R-07 | Requirement changes | Project | Business Analyst | 50% | 3 | 1.5 | Frequent stakeholder review | In Progress
R-08 | Security vulnerability | Security | IT Team | 20% | 5 | 1 | Patch management | Open
R-09 | Supplier bankruptcy | Operational | Procurement | 10% | 4 | 0.4 | Secondary supplier | Open
R-10 | Delayed approvals | Governance | Sponsor | 30% | 2 | 0.6 | Escalation process | In Progress

## 5x5 Risk Matrix
| 1 | 2 | 3 | 4 | 5
81-100%
61-80%
41-60%
21-40% |  | R-10 | R-02, R-04 | R-05
0-20% | R-09 |  | R-06 | R-01, R-08