## Risk Register
Risk ID | Risk Description | Category | Owner | Probability (P) | Impact (I) | PI Score | Mitigation Plan | Status
R-01 | Data breach | Security | IT Team | 10% | 5 | 0.5 | Implement firewall | Open
R-02 | Vendor delay | Operational | Operations | 30% | 3 | 0.9 | Backup vendor | In Progress
R-03 | Budget overrun | Financial | Finance | 50% | 4 | 2 | Weekly review | Closed
R-04 | AWS downtime | Operational | IT Team | 30% | 3 | 0.9 | More avaiiablity zones | In Progress

## 5x5 Risk Matrix
| 1 | 2 | 3 | 4 | 5
81-100%
61-80%
41-60% |  |  |  | R-03
21-40% |  |  | R-02, R-04
0-20% |  |  |  |  | R-01